## Action Log
Task | Owner | Priority | Status | Due date | Notes | Project name | Client name | Ticket/Project | Source
Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - confirm resolution after 24h window | Alex Thompson | High | In Progress | 2026-06-02 | Awaiting confirmation that external delivery is restored for 12 affected users after DNS change. | Office 365 email delivery failure affecting sales team | Northwood Manufacturing | Ticket | Office 365 email deliver…
Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout to remaining 8 accounts | Jamie Clarke | Medium | In Progress | 2026-06-05 | Blocked on procurement sign-off for remote workers without smartphones. | MFA rollout - remaining 8 user accounts | Northwood Manufacturing | Ticket | MFA rollout - remaining …
Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June | Alex Thompson | Medium | In Progress | 2026-06-09 | Migration window agreed; pre-migration config review complete. | Firewall migration to Fortigate 200F | Bridgewater Council | Ticket | Firewall migration to Fo…
Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation | Jamie Clarke | Medium | In Progress | 2026-06-11 | Phase 1 complete; Phase 2 (archive) to start next week. | SharePoint migration - planning department | Bridgewater Council | Ticket | SharePoint migration - p…
Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval | Alex Thompson | High | In Progress | 2026-06-14 | Awaiting partner sign-off after successful SQL migration test. | Case management system upgrade - v8.2 | Acme Legal LLP | Ticket | Case management system u…
Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June | Alex Thompson | Medium | In Progress | 2026-06-18 | Number porting submitted; training scheduled for week commencing 23 June. | VoIP system replacement - head office | Crown Oil Ltd | Ticket | VoIP system replacement …
Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation | Alex Thompson | High | In Progress | 2026-06-21 | One remediation item outstanding for CE+ recertification; deadline 15 June. | Cyber Essentials recertification | Hartley and Sons | Ticket | Cyber Essentials recerti…
Generated by Handover · gethandover.uk · 2026-05-28

## Risk Log
Risk | Impact | Mitigation | Status | Owner | Priority | RAG | Project name | Client name | Source
Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues. | Continued disruption to external communications for 12 sales users, potential loss of business. | Monitor delivery for 24h post-DNS change and escalate if failures persist. | Open | TBC | Medium |  | Office 365 email delivery failure affecting sales team | Northwood Manufacturing | Office 365 email deliver…
MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement. | Security risk from incomplete MFA coverage; 8 accounts remain vulnerable. | Chase procurement for hardware tokens and complete rollout. | Blocked | TBC | Medium |  | MFA rollout - remaining 8 user accounts | Northwood Manufacturing | MFA rollout - remaining …
Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes. | Extended exposure on unsupported Cisco ASA; risk to network security. | Confirm all pre-migration checks and maintain close coordination with council IT. | Open | TBC | Medium |  | Firewall migration to Fortigate 200F | Bridgewater Council | Firewall migration to Fo…
SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise. | Delayed access to archived planning documents; potential impact on department operations. | Coordinate schedule and validate data integrity throughout migration. | Open | TBC | Medium |  | SharePoint migration - planning department | Bridgewater Council | SharePoint migration - p…
Case management system upgrade delayed pending partner sign-off. | Missed upgrade window; potential disruption to legal operations. | Follow up for timely approval and prepare for rapid deployment. | Open | TBC | Medium |  | Case management system upgrade - v8.2 | Acme Legal LLP | Case management system u…
VoIP system go-live could slip if number porting or user training is delayed. | Head office may experience telephony disruption or user confusion. | Monitor porting progress and ensure training is delivered as scheduled. | Open | TBC | Medium |  | VoIP system replacement - head office | Crown Oil Ltd | VoIP system replacement …
Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline. | Failure to achieve CE+ certification; reputational and compliance impact. | Chase IT manager for approval and close remaining remediation item promptly. | Complete | TBC | Medium |  | Cyber Essentials recertification | Hartley and Sons | Cyber Essentials recerti…
Generated by Handover · gethandover.uk · 2026-05-28

## Executive Summary
Handover
Report generated: 2026-05-28 · Handover
Project: | Office 365 email delivery failure affecting sales team, MFA rollout - remaining 8 user accounts, Firewall migration to Fortigate 200F, SharePoint migration - planning department, Case management system upgrade - v8.2, VoIP system replacement - head office, Cyber Essentials recertification
Client: | Northwood Manufacturing, Bridgewater Council, Acme Legal LLP, Crown Oil Ltd, Hartley and Sons
Date: | 2026-05-28
Status: | Amber
Summary
Delivery across the portfolio is progressing, with several high-priority items requiring attention. Northwood Manufacturing awaits confirmation that outbound email delivery is restored for their sales team, and the MFA rollout is still blocked for three remote users pending hardware token approval. Bridgewater Council's firewall migration and SharePoint archive phase are on track, while Acme Legal LLP's case management upgrade is waiting on partner sign-off. Crown Oil Ltd is preparing for a major VoIP system cutover, and Hartley and Sons must close an MFA gap to complete Cyber Essentials recertification.
Key Actions
• Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - confirm resolution after 24h window - Alex Thompson
• Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout to remaining 8 accounts - Jamie Clarke
• Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June - Alex Thompson
• Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation - Jamie Clarke
• Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval - Alex Thompson
• Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June - Alex Thompson
• Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation - Alex Thompson
Key Risks
• Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues. - Continued disruption to external communications for 12 sales users, potential loss of business.
• MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement. - Security risk from incomplete MFA coverage; 8 accounts remain vulnerable.
• Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes. - Extended exposure on unsupported Cisco ASA; risk to network security.
• SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise. - Delayed access to archived planning documents; potential impact on department operations.
• Case management system upgrade delayed pending partner sign-off. - Missed upgrade window; potential disruption to legal operations.
• VoIP system go-live could slip if number porting or user training is delayed. - Head office may experience telephony disruption or user confusion.
• Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline. - Failure to achieve CE+ certification; reputational and compliance impact.
Next Steps
• Confirm successful delivery after 24h monitoring
• Close ticket if no further issues
• ---
• MFA rollout - remaining 8 user accounts - Northwood Manufacturing
• Status: Awaiting Client ¦ Owner: Jamie Clarke ¦ RAG: Amber
Generated by Handover · gethandover.uk · 2026-05-28

## Status Report
Ticket / Project | Client | Status | Owner | RAG | Progress | Actions | Next Steps
Office 365 email delivery failure affecting sales team | Northwood Manufacturing | In Progress | Alex Thompson | Amber | SPF record updated to include Microsoft 365. DNS changes have propagated and a 24-hour monitoring window is underway to confirm restored outbound delivery for 12 affected users. Actions 1. Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - Alex Thompson - High Risks 1. Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues. Impact: Continued disruption to external communications for 12 sales users, potential loss of business. Mitigation: Monitor delivery for 24h post-DNS change and escalate if failures persist. Next Steps 1. Confirm successful delivery after 24h monitoring 2. Close ticket if no further issues
MFA rollout - remaining 8 user accounts | Northwood Manufacturing | Awaiting Client | Jamie Clarke | Amber | Hardware token alternative proposed for 3 remote users without smartphones. Awaiting procurement approval to complete MFA rollout for 8 outstanding accounts. Actions 1. Chase procurement approval for hardware token MFA alternative for 3 remote users - Jamie Clarke - Medium Risks 1. MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement. Impact: Security risk from incomplete MFA coverage; 8 accounts remain vulnerable. Mitigation: Chase procurement for hardware tokens and complete rollout. Next Steps 1. Procure hardware tokens 2. Complete MFA rollout to all remaining accounts
Firewall migration to Fortigate 200F | Bridgewater Council | In Progress | Alex Thompson | Amber | Pre-migration configuration review is complete. VPN tunnels have been documented and the migration window is agreed for Saturday 14 June. Change request approved by council IT lead. Actions 1. Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June - Alex Thompson - Medium Risks 1. Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes. Impact: Extended exposure on unsupported Cisco ASA; risk to network security. Mitigation: Confirm all pre-migration checks and maintain close coordination with council IT. Next Steps 1. Finalise migration checklist 2. Execute migration as scheduled
SharePoint migration - planning department | Bridgewater Council | In Progress | Jamie Clarke | Amber | Phase 1 (active projects) complete with 847GB migrated. Phase 2 (archive) scheduled to begin next week. Actions 1. Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation - Jamie Clarke - Medium Risks 1. SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise. Impact: Delayed access to archived planning documents; potential impact on department operations. Mitigation: Coordinate schedule and validate data integrity throughout migration. Next Steps 1. Start Phase 2 migration 2. Validate migrated data
Case management system upgrade - v8.2 | Acme Legal LLP | Awaiting Client | Alex Thompson | Amber | SQL migration tested successfully in staging. Awaiting partner sign-off before proceeding to production deployment. Actions 1. Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval - Alex Thompson - High Risks 1. Case management system upgrade delayed pending partner sign-off. Impact: Missed upgrade window; potential disruption to legal operations. Mitigation: Follow up for timely approval and prepare for rapid deployment. Next Steps 1. Obtain partner sign-off 2. Schedule production deployment
VoIP system replacement - head office | Crown Oil Ltd | In Progress | Alex Thompson | Amber | SBC configured and number porting submitted to carrier. User training sessions scheduled for week commencing 23 June. Go-live target is 30 June. Actions 1. Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June - Alex Thompson - Medium Risks 1. VoIP system go-live could slip if number porting or user training is delayed. Impact: Head office may experience telephony disruption or user confusion. Mitigation: Monitor porting progress and ensure training is delivered as scheduled. Next Steps 1. Monitor number porting status 2. Deliver user training 3. Prepare for go-live
Cyber Essentials recertification | Hartley and Sons | In Progress | Alex Thompson | Amber | Three of four remediation items completed for CE+ recertification. Outstanding item is closing the MFA gap on two admin accounts, currently with client IT manager for approval. Actions 1. Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation - Alex Thompson - High Risks 1. Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline. Impact: Failure to achieve CE+ certification; reputational and compliance impact. Mitigation: Chase IT manager for approval and close remaining remediation item promptly. Next Steps 1. Obtain approval and close MFA gap 2. Submit for recertification
Generated by Handover · gethandover.uk · 2026-05-28

## RAID Log
ID | Type | Description | Owner | Impact | Probability | Status | Action Required | Due Date | Client | Date Added
RSK-001 | Risk | Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues. | Alex Thompson | Continued disruption to external communications for 12 sales users, potential loss of business. | Medium | Open | Monitor delivery for 24h post-DNS change and escalate if failures persist. | 2026-05-28 | Northwood Manufacturing | 2026-05-28
RSK-002 | Risk | MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement. | Alex Thompson | Security risk from incomplete MFA coverage; 8 accounts remain vulnerable. | Medium | Open | Chase procurement for hardware tokens and complete rollout. | 2026-05-28 | Northwood Manufacturing | 2026-05-28
RSK-003 | Risk | Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes. | Alex Thompson | Extended exposure on unsupported Cisco ASA; risk to network security. | Medium | Open | Confirm all pre-migration checks and maintain close coordination with council IT. | 2026-05-28 | Bridgewater Council | 2026-05-28
RSK-004 | Risk | SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise. | Alex Thompson | Delayed access to archived planning documents; potential impact on department operations. | Medium | Open | Coordinate schedule and validate data integrity throughout migration. | 2026-05-28 | Bridgewater Council | 2026-05-28
RSK-005 | Risk | Case management system upgrade delayed pending partner sign-off. | Alex Thompson | Missed upgrade window; potential disruption to legal operations. | Medium | Open | Follow up for timely approval and prepare for rapid deployment. | 2026-05-28 | Acme Legal LLP | 2026-05-28
RSK-006 | Risk | VoIP system go-live could slip if number porting or user training is delayed. | Alex Thompson | Head office may experience telephony disruption or user confusion. | Medium | Open | Monitor porting progress and ensure training is delivered as scheduled. | 2026-05-28 | Crown Oil Ltd | 2026-05-28
RSK-007 | Risk | Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline. | Alex Thompson | Failure to achieve CE+ certification; reputational and compliance impact. | Medium | Open | Chase IT manager for approval and close remaining remediation item promptly. | 2026-05-28 | Hartley and Sons | 2026-05-28
Generated by Handover · gethandover.uk · 2026-05-28

## Change Log
Change ID | Date | Description | Requested By | Impact | Status | Owner | Notes
CHG-001 | 2026-05-28 | Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - confirm resolution after 24h window | Northwood Manufacturing | High | Proposed | Alex Thompson | Awaiting confirmation that external delivery is restored for 12 affected users after DNS change.
CHG-002 | 2026-05-28 | Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout to remaining 8 accounts | Northwood Manufacturing | Medium | Proposed | Jamie Clarke | Blocked on procurement sign-off for remote workers without smartphones.
CHG-003 | 2026-05-28 | Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June | Bridgewater Council | Medium | Proposed | Alex Thompson | Migration window agreed; pre-migration config review complete.
CHG-004 | 2026-05-28 | Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation | Bridgewater Council | Medium | Proposed | Jamie Clarke | Phase 1 complete; Phase 2 (archive) to start next week.
CHG-005 | 2026-05-28 | Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval | Acme Legal LLP | High | Proposed | Alex Thompson | Awaiting partner sign-off after successful SQL migration test.
CHG-006 | 2026-05-28 | Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June | Crown Oil Ltd | Medium | Proposed | Alex Thompson | Number porting submitted; training scheduled for week commencing 23 June.
CHG-007 | 2026-05-28 | Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation | Hartley and Sons | High | Proposed | Alex Thompson | One remediation item outstanding for CE+ recertification; deadline 15 June.
Generated by Handover · gethandover.uk · 2026-05-28

## Stakeholder Update
Overall Status: | Amber
Project: | Office 365 email delivery failure affecting sales team, MFA rollout - remaining 8 user accounts, Firewall migration to Fortigate 200F, SharePoint migration - planning department, Case management system upgrade - v8.2, VoIP system replacement - head office, Cyber Essentials recertification
Client: | Northwood Manufacturing, Bridgewater Council, Acme Legal LLP, Crown Oil Ltd, Hartley and Sons
Period: | 2026-05-28
Highlights This Period
• Delivery across the portfolio is progressing, with several high-priority items requiring attention
• Northwood Manufacturing awaits confirmation that outbound email delivery is restored for their sales team, and the MFA rollout is still blocked for three remote users pending hardware token approval
• Bridgewater Council's firewall migration and SharePoint archive phase are on track, while Acme Legal LLP's case management upgrade is waiting on partner sign-off
• Crown Oil Ltd is preparing for a major VoIP system cutover, and Hartley and Sons must close an MFA gap to complete Cyber Essentials recertification.
Items Requiring Attention
• Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues.
• MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement.
• Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes.
• SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise.
• Case management system upgrade delayed pending partner sign-off.
• VoIP system go-live could slip if number porting or user training is delayed.
• Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline.
Upcoming Actions
• Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - confirm resolution after 24h window - Alex Thompson
• Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout to remaining 8 accounts - Jamie Clarke
• Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June - Alex Thompson
• Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation - Jamie Clarke
• Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval - Alex Thompson
• Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June - Alex Thompson
• Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation - Alex Thompson
For Information Only
This update was auto-generated by Handover. Please direct any queries to your account manager.
Generated by Handover · gethandover.uk · 2026-05-28

## Meeting Notes
Ticket / Project | Client | Quick Summary | Key Wins | Risks | Talking Points | Actions
Office 365 email delivery failure affecting sales team | Northwood Manufacturing | 2 open action(s) for Northwood Manufacturing. 2 risk(s) identified. Review progress and agree next steps. | No completed actions this period — review progress on open items. | • Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues. Impact: Continued disruption to external communications for 12 sales users, potential loss of business. Mitigation: Monitor delivery for 24h post-DNS change and escalate if failures persist. • MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement. Impact: Security risk from incomplete MFA coverage; 8 accounts remain vulnerable. Mitigation: Chase procurement for hardware tokens and complete rollout. | • Review status of: Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - confirm resolution after 24h window • Review status of: Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout to remaining 8 accounts • Discuss risk mitigation for 2 open risk(s) • Confirm next steps and ownership for outstanding items • Agree timeline for resolution | • Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - confirm resolution after 24h window — Owner: Alex Thompson — High priority • Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout to remaining 8 accounts — Owner: Jamie Clarke — Medium priority
Firewall migration to Fortigate 200F | Bridgewater Council | 2 open action(s) for Bridgewater Council. 2 risk(s) identified. Review progress and agree next steps. | No completed actions this period — review progress on open items. | • Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes. Impact: Extended exposure on unsupported Cisco ASA; risk to network security. Mitigation: Confirm all pre-migration checks and maintain close coordination with council IT. • SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise. Impact: Delayed access to archived planning documents; potential impact on department operations. Mitigation: Coordinate schedule and validate data integrity throughout migration. | • Review status of: Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June • Review status of: Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation • Discuss risk mitigation for 2 open risk(s) • Confirm next steps and ownership for outstanding items • Agree timeline for resolution | • Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June — Owner: Alex Thompson — Medium priority • Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation — Owner: Jamie Clarke — Medium priority
Case management system upgrade - v8.2 | Acme Legal LLP | 1 open action(s) for Acme Legal LLP. 1 risk(s) identified. Review progress and agree next steps. | No completed actions this period — review progress on open items. | • Case management system upgrade delayed pending partner sign-off. Impact: Missed upgrade window; potential disruption to legal operations. Mitigation: Follow up for timely approval and prepare for rapid deployment. | • Review status of: Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval • Discuss risk mitigation for 1 open risk(s) • Confirm next steps and ownership for outstanding items • Agree timeline for resolution | • Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval — Owner: Alex Thompson — High priority
VoIP system replacement - head office | Crown Oil Ltd | 1 open action(s) for Crown Oil Ltd. 1 risk(s) identified. Review progress and agree next steps. | No completed actions this period — review progress on open items. | • VoIP system go-live could slip if number porting or user training is delayed. Impact: Head office may experience telephony disruption or user confusion. Mitigation: Monitor porting progress and ensure training is delivered as scheduled. | • Review status of: Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June • Discuss risk mitigation for 1 open risk(s) • Confirm next steps and ownership for outstanding items • Agree timeline for resolution | • Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June — Owner: Alex Thompson — Medium priority
Cyber Essentials recertification | Hartley and Sons | 1 open action(s) for Hartley and Sons. 1 risk(s) identified. Review progress and agree next steps. | No completed actions this period — review progress on open items. | • Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline. Impact: Failure to achieve CE+ certification; reputational and compliance impact. Mitigation: Chase IT manager for approval and close remaining remediation item promptly. | • Review status of: Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation • Discuss risk mitigation for 1 open risk(s) • Confirm next steps and ownership for outstanding items • Agree timeline for resolution | • Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation — Owner: Alex Thompson — High priority
Generated by Handover · gethandover.uk · 2026-05-28

## Invoice Time Summary
Ticket/Project | Client | Engineer | Hours | Date | Description of Work | Rate (£) | Total (£)
Office 365 email delivery failure affecting sales team | Northwood Manufacturing | Alex Thompson | 0.00 | 2026-05-28 | Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update - confirm resolution after 24h window
MFA rollout - remaining 8 user accounts | Northwood Manufacturing | Jamie Clarke | 0.00 | 2026-05-28 | Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout to remaining 8 accounts
Firewall migration to Fortigate 200F | Bridgewater Council | Alex Thompson | 0.00 | 2026-05-28 | Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for 14 June
SharePoint migration - planning department | Bridgewater Council | Jamie Clarke | 0.00 | 2026-05-28 | Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data validation
Case management system upgrade - v8.2 | Acme Legal LLP | Alex Thompson | 0.00 | 2026-05-28 | Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production deployment upon approval
VoIP system replacement - head office | Crown Oil Ltd | Alex Thompson | 0.00 | 2026-05-28 | Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-live 30 June
Cyber Essentials recertification | Hartley and Sons | Alex Thompson | 0.00 | 2026-05-28 | Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essentials remediation
TOTAL
Generated by Handover · gethandover.uk · 2026-05-28

## Communication Log
Date | From | To | Channel | Summary | Follow Up Required | Status
2026-05-28 | Alex Thompson | Client | HaloPSA / Email | Monitor Office 365 outbound email delivery for sales@northwoodmfg.co.uk following SPF record update | No | Pending
2026-05-28 | Jamie Clarke | Client | HaloPSA / Email | Chase procurement approval for hardware token MFA alternative for 3 remote users - complete rollout | No | Pending
2026-05-28 | Alex Thompson | Client | HaloPSA / Email | Prepare for Fortigate 200F migration - confirm pre-migration checks and schedule with council IT for | No | Pending
2026-05-28 | Jamie Clarke | Client | HaloPSA / Email | Begin SharePoint migration Phase 2 (archive) for planning department - coordinate schedule and data | No | Pending
2026-05-28 | Alex Thompson | Client | HaloPSA / Email | Follow up with partner for sign-off on Osprey case management system upgrade - proceed to production | No | Pending
2026-05-28 | Alex Thompson | Client | HaloPSA / Email | Complete number porting and deliver user training for Teams Direct Routing VoIP system - target go-l | No | Pending
2026-05-28 | Alex Thompson | Client | HaloPSA / Email | Chase client IT manager for approval to close MFA gap on 2 admin accounts - finalise Cyber Essential | No | Pending
Generated by Handover · gethandover.uk · 2026-05-28

## Project Health Dashboard
OVERALL STATUS
Amber
Metric | Value | Status
Open Actions | 7 | Amber
Risks Identified | 7 | Amber
Hours Logged | 0.00 | Neutral
Tickets in Scope | 7 | Neutral
Clients Covered | 5 | Neutral
Project Status | In Progress | Neutral
Target Date | 02 Jun 2026 | Neutral
Days Since Last Update | 0 | Neutral
Generated by Handover · gethandover.uk · 2026-05-28

## Detailed Risk Register
Risk ID | Category | Description | Likelihood (1-5) | Impact (1-5) | Risk Score | RAG | Owner | Mitigation | Contingency | Review Date | Status
RSK-001 | General | Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues. | 3 | 3 | 9 | Amber | Alex Thompson | Monitor delivery for 24h post-DNS change and escalate if failures persist. | To be defined | 2026-05-28 | Open
RSK-002 | General | MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement. | 3 | 3 | 9 | Amber | Alex Thompson | Chase procurement for hardware tokens and complete rollout. | To be defined | 2026-05-28 | Open
RSK-003 | Technical | Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes. | 3 | 3 | 9 | Amber | Alex Thompson | Confirm all pre-migration checks and maintain close coordination with council IT. | To be defined | 2026-05-28 | Open
RSK-004 | General | SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise. | 3 | 3 | 9 | Amber | Alex Thompson | Coordinate schedule and validate data integrity throughout migration. | To be defined | 2026-05-28 | Open
RSK-005 | General | Case management system upgrade delayed pending partner sign-off. | 3 | 3 | 9 | Amber | Alex Thompson | Follow up for timely approval and prepare for rapid deployment. | To be defined | 2026-05-28 | Open
RSK-006 | General | VoIP system go-live could slip if number porting or user training is delayed. | 3 | 3 | 9 | Amber | Alex Thompson | Monitor porting progress and ensure training is delivered as scheduled. | To be defined | 2026-05-28 | Open
RSK-007 | General | Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline. | 3 | 3 | 9 | Amber | Alex Thompson | Chase IT manager for approval and close remaining remediation item promptly. | To be defined | 2026-05-28 | Open
Generated by Handover · gethandover.uk · 2026-05-28

## PESTLE Analysis
Category | Factor | Description | Impact | Likelihood | Mitigation | Relevance (H/M/L)
Political | Data Protection Regulations | GDPR compliance requirements for data handling | High if not compliant | Medium | Ensure all data processing follows GDPR guidelines | H
Economic | IT Budget Constraints | Budget limitations may affect scope or timeline | Schedule delay if budget insufficient | Medium | Regular budget reviews and scope management | M
Social | Staff Adoption | End users may resist changes to systems and workflows | Reduced effectiveness of implemented solutions | Medium | Training and change management plan | M
Technological | System Compatibility | New systems must integrate with existing infrastructure | Technical failures if incompatible | Low | Compatibility testing before deployment | H
Legal | Software Licensing | All software must be properly licensed | Legal liability if unlicensed software used | Low | Regular licence audits | M
Environmental | Energy Consumption | IT infrastructure energy usage and sustainability | Reputational risk if not managed | Low | Consider energy efficient solutions | L
Generated by Handover · gethandover.uk · 2026-05-28

## Issue Log
Issue ID | Date Raised | Description | Raised By | Priority | Status | Owner | Resolution | Date Resolved | Client
ISS-001 | 2026-05-28 | Office 365 outbound email delivery may still fail for sales team if SPF/DKIM changes do not fully resolve propagation issues. | Northwood Manufacturing | Medium | Open | Alex Thompson |  |  | Northwood Manufacturing
ISS-002 | 2026-05-28 | MFA rollout blocked for 3 remote users without smartphones, delaying full enforcement. | Northwood Manufacturing | Medium | Open | Alex Thompson |  |  | Northwood Manufacturing
ISS-003 | 2026-05-28 | Firewall migration may be delayed if pre-migration checks identify further issues or if council IT availability changes. | Bridgewater Council | Medium | Open | Alex Thompson |  |  | Bridgewater Council
ISS-004 | 2026-05-28 | SharePoint migration Phase 2 (archive) could overrun if data validation or scheduling conflicts arise. | Bridgewater Council | Medium | Open | Alex Thompson |  |  | Bridgewater Council
ISS-005 | 2026-05-28 | Case management system upgrade delayed pending partner sign-off. | Acme Legal LLP | Medium | Open | Alex Thompson |  |  | Acme Legal LLP
ISS-006 | 2026-05-28 | VoIP system go-live could slip if number porting or user training is delayed. | Crown Oil Ltd | Medium | Open | Alex Thompson |  |  | Crown Oil Ltd
ISS-007 | 2026-05-28 | Cyber Essentials recertification at risk if MFA gap for admin accounts is not closed before deadline. | Hartley and Sons | Medium | Open | Alex Thompson |  |  | Hartley and Sons
Generated by Handover · gethandover.uk · 2026-05-28

## Decisions Log
Decision ID | Date | Decision | Decision Maker | Rationale | Impact | Alternatives Considered | Status
DEC-001 | 27 May 2026 | Proceed with 24h monitoring for Office 365 email issue | Alex Thompson | DNS changes require time to propagate | Ensures issue is fully resolved before closure | Immediate closure | Implemented
DEC-002 | 27 May 2026 | Use hardware tokens for remote MFA users | Jamie Clarke | Remote users cannot use smartphone apps | Enables full MFA coverage | Wait for procurement | Proposed
DEC-003 | 27 May 2026 | Maintain migration schedule for Bridgewater Council firewall | Alex Thompson | Pre-migration checks complete | Keeps project on track | Reschedule if issues found | Approved
DEC-004 | 27 May 2026 | Await partner sign-off for Acme Legal LLP upgrade | Alex Thompson | Partner approval required for production deployment | Avoids unplanned disruption | Proceed without approval | Proposed
Generated by Handover · gethandover.uk · 2026-05-28

## Lessons Learned
Category | What Went Well | What Could Improve | Root Cause | Recommendation | Owner | Status
Risk Management | Risks identified early in the process | Earlier mitigation planning | Reactive risk identification | Implement risk register from project start | Alex Thompson | Identified
Planning | Clear action items defined | Earlier assignment of owners | Ownership assigned later than ideal | Assign owners during initial triage | Alex Thompson | Identified
Communication | Regular updates provided to stakeholders | More structured meeting cadence | Ad hoc update rhythm | Schedule regular project standups | Alex Thompson | Identified
Generated by Handover · gethandover.uk · 2026-05-28